## Sprint Overview
Sprint | Week | Sprint Goal | Key Epics / Work Streams
Sprint 1 | Week 1 | Lay the foundation: accounts, authentication, patient and provider profiles, design system. Front-end also starts building the Search Results and Provider Details pages against mock data. | E1 (partial), E2 (partial), E3 (partial), E4/E5 (UI shell only), E10 (partial), Design, Analytics, QA, PM
Sprint 2 | Week 2 | Search, provider availability, and license verification; wire the Sprint 1 mock UI to real endpoints | E3 (license submission), E9 (license review), E6, E4, E5, E10, Design, Analytics, QA, PM
Sprint 3 | Week 3 | End-to-end integration of pages 1-3, account management, password reset, onboarding for Vanya | E1 (password reset), E9 (account management), E10 (final), Integration, Design, Analytics, QA, PM
Sprint 4 | Week 4 | Appointment booking, appointment management, stabilization and release prep | E7, E8, E2 (remainder), E6 (remainder), Support, Design, Analytics, QA, PM

## Sprint Backlog
# | Sprint | Epic | Label | Type | Summary (issue) | Assignee | Role | Note
1 | Sprint 1 | Design | design | Task | Wireframes for the 4 site pages | Illia | Designer (UI/UX)
2 | Sprint 1 | Design | design | Task | UI kit (colors, typography, base components) | Illia | Designer (UI/UX)
3 | Sprint 1 | E1 | E1-S1 | Story | As a user, I want to register with email and password, so that I can get access to the platform.
4 | Sprint 1 | E1 | E1-S1 | Task | Build the registration API (backend) | Marika | Backend Developer
5 | Sprint 1 | E1 | E1-S1 | Sub-task | Validate email format and minimum password requirements | Marika | Backend Developer
6 | Sprint 1 | E1 | E1-S1 | Sub-task | Hash the password before storing it in the database | Marika | Backend Developer
7 | Sprint 1 | E1 | E1-S1 | Sub-task | Check for duplicate email addresses | Marika | Backend Developer
8 | Sprint 1 | E1 | E1-S1 | Task | Build the registration form (frontend) | Yana | Front-end Developer
9 | Sprint 1 | E1 | E1-S1 | Sub-task | Client-side field validation | Yana | Front-end Developer
10 | Sprint 1 | E1 | E1-S1 | Sub-task | Handle and display API errors | Yana | Front-end Developer
11 | Sprint 1 | E1 | E1-S2 | Story | As a user, I want to choose my role during registration (patient / provider), so that the system shows me the right functionality.
12 | Sprint 1 | E1 | E1-S2 | Task | Add a "role" field to the user model | Marika | Backend Developer
13 | Sprint 1 | E1 | E1-S2 | Task | Implement a role switch on the registration form | Yana | Front-end Developer
14 | Sprint 1 | E1 | E1-S3 | Story | As a user, I want to log in, so that I can reach my personal cabinet.
15 | Sprint 1 | E1 | E1-S3 | Task | Login API that issues a token/session | Marika | Backend Developer
16 | Sprint 1 | E1 | E1-S3 | Sub-task | Basic rate limiting on failed login attempts | Marika | Backend Developer
17 | Sprint 1 | E1 | E1-S3 | Task | Login form (frontend) | Yaroslav | Front-end Developer
18 | Sprint 1 | E1 | E1-S4 | Story | As a user, I want to log out, so that I can protect my account on a shared device.
19 | Sprint 1 | E1 | E1-S4 | Task | Implement logout (invalidate token/session) | Marika | Backend Developer
20 | Sprint 1 | E1 | E1-S5 | Story | As a user, I want to reset my password if I forget it.
21 | Sprint 1 | E1 | E1-S5 | Task | New-password form (frontend) | Yaroslav | Front-end Developer | Backend tasks for this story moved to Sprint 3 - see rebalancing note
22 | Sprint 1 | E2 | E2-S1 | Story | As a patient, I want to create and edit my profile, so that the provider and the system see up-to-date information about me.
23 | Sprint 1 | E2 | E2-S1 | Task | Patient profile CRUD API | Marika | Backend Developer
24 | Sprint 1 | E2 | E2-S1 | Task | Profile create/edit form (UI) | Yana | Front-end Developer
25 | Sprint 1 | E2 | E2-S2 | Story | As a patient, I want to specify my location, so that I get relevant search results.
26 | Sprint 1 | E2 | E2-S2 | Task | Text field for location + save it to the profile | Yaroslav | Front-end Developer
27 | Sprint 1 | E2 | E2-S3 | Story | As a patient, I want to specify the language(s) I speak, so that I can find a provider I can communicate with.
28 | Sprint 1 | E2 | E2-S3 | Task | Multi-select language field in the profile | Yaroslav | Front-end Developer
29 | Sprint 1 | E2 | E2-S4 | Story | As a patient, I want to optionally specify my pregnancy week, giving explicit consent to its processing.
30 | Sprint 1 | E2 | E2-S4 | Task | "Pregnancy week" field + a separate explicit-consent checkbox | Yaroslav | Front-end Developer
31 | Sprint 1 | E2 | E2-S4 | Sub-task | Explanatory text on why this data is collected and how it is used | Anna | PM
32 | Sprint 1 | E3 | E3-S1 | Story | As a provider, I want to create and edit a profile (name, specialization, address, languages, description, contacts).
33 | Sprint 1 | E3 | E3-S1 | Task | Provider profile CRUD API | Marika | Backend Developer
34 | Sprint 1 | E3 | E3-S1 | Task | Provider profile form (UI) | Yana | Front-end Developer
35 | Sprint 1 | E3 | E3-S2 | Story | As a provider, I want to list the services I offer, so that patients can select them when booking.
36 | Sprint 1 | E3 | E3-S2 | Task | "Service" model (name, duration) | Marika | Backend Developer
37 | Sprint 1 | E3 | E3-S2 | Task | UI to manage the list of services (add/edit/remove) | Yana | Front-end Developer
38 | Sprint 1 | E4 | E4-S1 | Task | Search results page UI with a filter panel | Yaroslav | Front-end Developer | Built against mock data and Sprint 1 wireframes; wired to the live endpoint in Sprint 2
39 | Sprint 1 | E5 | E5-S1 | Task | Provider profile page UI | Yaroslav | Front-end Developer | Built against mock data and Sprint 1 wireframes; wired to the live endpoint in Sprint 2
40 | Sprint 1 | E10 | E10-S1 | Story | As the product owner, I want passwords never to be stored in plain text, so that a data breach has minimal impact.
41 | Sprint 1 | E10 | E10-S1 | Task | Set up password hashing (bcrypt/argon2) | Marika | Backend Developer
42 | Sprint 1 | E10 | E10-S2 | Story | As the product owner, I want access to data to be separated by role, so that patients, providers, and the administrator only see what they are authorized to see.
43 | Sprint 1 | E10 | E10-S2 | Task | Implement RBAC middleware on the backend for the three roles | Marika | Backend Developer
44 | Sprint 1 | E10 | E10-S4 | Story | As the product owner, I want data to be transmitted and stored encrypted.
45 | Sprint 1 | E10 | E10-S4 | Task | Set up HTTPS/TLS at the hosting level | Marika | Backend Developer
46 | Sprint 1 | Analytics | analytics | Task | Define key success metrics for the MVP | Oksana | Data Analyst
47 | Sprint 1 | QA | qa | Task | Test cases for E1 (Registration & Authentication) | Iryna | QA
48 | Sprint 1 | QA | qa | Task | Test cases for E2-E3 (profiles) | Iryna | QA
49 | Sprint 1 | QA | qa | Task | Testing of E1 features as they land | Iryna | QA
50 | Sprint 1 | PM | pm | Task | Sprint planning & backlog grooming (Sprint 1) | Anna | PM
51 | Sprint 1 | PM | pm | Task | Align wireframes and UI kit with the team | Anna | PM
52 | Sprint 2 | E9 | E9-S1 | Story | As a site administrator, I want to see a queue of providers awaiting license verification and approve or reject their registration.
53 | Sprint 2 | E9 | E9-S1 | Task | API for the queue of provider verification requests | Marika | Backend Developer
54 | Sprint 2 | E9 | E9-S1 | Task | License review queue UI with "Approve"/"Reject" actions | Yana | Front-end Developer
55 | Sprint 2 | E3 | E3-S3 | Story | As a provider, I want to submit my medical license data, so that the site administrator can verify me before my profile is published. |  |  | Moved from Sprint 1 to rebalance backend workload and ship together with E9-S1
56 | Sprint 2 | E3 | E3-S3 | Task | A field/upload for the license document or number | Marika | Backend Developer
57 | Sprint 2 | E3 | E3-S3 | Sub-task | Validate file format and size | Marika | Backend Developer
58 | Sprint 2 | E3 | E3-S3 | Task | Provider profile status: "Pending" / "Approved" / "Rejected" | Marika | Backend Developer
59 | Sprint 2 | E3 | E3-S3 | Sub-task | The profile is not shown in public search until the status is "Approved" | Marika | Backend Developer
60 | Sprint 2 | E6 | E6-S1 | Story | As a provider, I want to define my working hours, so that patients see when I'm available. |  |  | Delivered together with E6-S1 tasks below
61 | Sprint 2 | E6 | E6-S1 | Story | As a provider, I want to create available time slots based on my schedule.
62 | Sprint 2 | E6 | E6-S1 | Story | As a provider, I want to mark specific dates/times as unavailable (vacation, sick leave, etc.).
63 | Sprint 2 | E6 | E6-S1 | Task | "Availability slot" model (provider, date, time, status) | Marika | Backend Developer
64 | Sprint 2 | E6 | E6-S1 | Task | Schedule/slots CRUD API | Marika | Backend Developer
65 | Sprint 2 | E6 | E6-S1 | Task | Availability calendar UI for the provider | Yana | Front-end Developer
66 | Sprint 2 | E4 | E4-S1 | Story | As a patient, I want to search for providers by location (text/city), so that I can find someone nearby. |  |  | Delivered together with E4-S1 tasks below
67 | Sprint 2 | E4 | E4-S1 | Story | As a patient, I want to filter by specialization and service, so that I find exactly what I need.
68 | Sprint 2 | E4 | E4-S1 | Story | As a patient, I want to filter by spoken language.
69 | Sprint 2 | E4 | E4-S1 | Story | As a patient, I want to filter by availability (has open slots soon).
70 | Sprint 2 | E4 | E4-S1 | Task | Backend search endpoint supporting combined filters (query params) | Marika | Backend Developer
71 | Sprint 2 | E4 | E4-S1 | Sub-task | Index the database fields used by the filters (performance) | Marika | Backend Developer
72 | Sprint 2 | E4 | E4-S1 | Task | Handle an empty result set (a "nothing found" UX message) | Yaroslav | Front-end Developer
73 | Sprint 2 | E4 | E4-S1 | Task | Connect the Search & Results UI to the live search endpoint | Yaroslav | Front-end Developer | Wires the Sprint 1 mock-data UI to the endpoint delivered this sprint
74 | Sprint 2 | E5 | E5-S1 | Story | As a patient, I want to open a provider's profile and see their basic information, services, location, languages, schedule, and available slots, so that I can decide whether to book.
75 | Sprint 2 | E5 | E5-S1 | Task | Endpoint returning full provider data together with available slots | Marika | Backend Developer
76 | Sprint 2 | E5 | E5-S1 | Task | Connect the Provider Details UI to the live provider endpoint | Yaroslav | Front-end Developer | Wires the Sprint 1 mock-data UI to the endpoint delivered this sprint
77 | Sprint 2 | E10 | E10-S5 | Story | As the product owner, I want baseline protection against common web attacks (OWASP Top 10), so that the risk of a personal-data leak is reduced.
78 | Sprint 2 | E10 | E10-S5 | Task | Validation and parameterized queries against SQL injection (A05 Injection) | Marika | Backend Developer
79 | Sprint 2 | E10 | E10-S5 | Task | A basic audit of the cloud environment's configuration (A02 Security Misconfiguration) | Marika | Backend Developer
80 | Sprint 2 | Design | design | Task | High-fidelity mockups: Search & Results, Provider Details, Dashboard (role views), License review queue | Illia | Designer (UI/UX)
81 | Sprint 2 | Analytics | analytics | Task | Event-tracking plan for the Search and Provider Details pages | Oksana | Data Analyst
82 | Sprint 2 | QA | qa | Task | Test cases for E4-E6, E9 | Iryna | QA
83 | Sprint 2 | QA | qa | Task | Testing of Sprint 1 features (regression #0) | Iryna | QA
84 | Sprint 2 | PM | pm | Task | Sprint planning (Sprint 2), review of Sprint 1 results | Anna | PM
85 | Sprint 2 | PM | pm | Task | Stakeholder/mentor communication on progress | Anna | PM
86 | Sprint 3 | E9 | E9-S2 | Story | As a site administrator, I want to add, deactivate, or remove user and provider accounts.
87 | Sprint 3 | E9 | E9-S2 | Task | Account management API (list/deactivate/delete) | Marika | Backend Developer
88 | Sprint 3 | E9 | E9-S2 | Task | UI listing users/providers with management actions | Yana | Front-end Developer
89 | Sprint 3 | E10 | E10-S3 | Story | As the product owner, I want access to sensitive medical data to be logged, so that incidents can be investigated.
90 | Sprint 3 | E10 | E10-S3 | Task | Implement an audit log for access to profiles and sensitive fields (e.g., pregnancy week) | Marika | Backend Developer
91 | Sprint 3 | E10 | E10-S4 | Task | Enable encryption at rest at the database/storage level | Marika | Backend Developer | Second task of Story E10-S4, started in Sprint 1
92 | Sprint 3 | E1 | E1-S5 | Task | "Forgot password" endpoint + generation of a one-time reset token | Marika | Backend Developer | Moved from Sprint 1 to rebalance backend workload
93 | Sprint 3 | E1 | E1-S5 | Task | Send the password-reset email (email service integration) | Marika | Backend Developer | Moved from Sprint 1 to rebalance backend workload
94 | Sprint 3 | Integration | integration | Task | End-to-end integration of the Search and Provider Details pages with the real API | Yaroslav | Front-end Developer
95 | Sprint 3 | Integration | integration | Task | End-to-end integration of profile forms and the admin panel with the real API | Yana | Front-end Developer
96 | Sprint 3 | Integration | integration | Task | Responsive/mobile layout: Home and Dashboard | Yana | Front-end Developer
97 | Sprint 3 | Integration | integration | Task | Responsive/mobile layout: Search and Provider Details | Yaroslav | Front-end Developer
98 | Sprint 3 | Design | design | Task | Visual QA of implemented UI vs. mockups | Illia | Designer (UI/UX)
99 | Sprint 3 | Design | design | Task | Booking-flow mockups (calendar, form, confirmation) for Sprint 4 | Illia | Designer (UI/UX)
100 | Sprint 3 | Analytics | analytics | Task | Implement event tracking on pages 1-3 together with front-end | Oksana | Data Analyst
101 | Sprint 3 | QA | qa | Task | Integration testing of Sprint 1-2 features | Iryna | QA
102 | Sprint 3 | QA | qa | Task | Regression testing #1 | Iryna | QA
103 | Sprint 3 | QA | qa | Task | Bug tracking / bug log maintenance | Iryna | QA
104 | Sprint 3 | PM | pm | Task | Onboarding plan and context for Vanya (booking domain, API contracts) | Anna | PM
105 | Sprint 3 | PM | pm | Task | Demo of pages 1-3 to stakeholders | Anna | PM
106 | Sprint 3 | PM | pm | Task | Risk management for the Sprint 4 workload | Anna | PM
107 | Sprint 4 | E7 | E7-S1 | Story | As a patient, I want to select a service, date, and time, and book an appointment. |  |  | Vanya joins the team
108 | Sprint 4 | E7 | E7-S1 | Task | Slot-booking API with transactional locking that prevents double booking | Vanya | Backend Developer | Vanya joins the team
109 | Sprint 4 | E7 | E7-S1 | Sub-task | Database-level lock/transaction mechanism during booking | Vanya | Backend Developer
110 | Sprint 4 | E7 | E7-S1 | Task | UI for selecting service/date/time and a "Book" button | Yaroslav | Front-end Developer
111 | Sprint 4 | E7 | E7-S2 | Story | As a patient, I want to receive an immediate confirmation after booking.
112 | Sprint 4 | E7 | E7-S2 | Task | In-app confirmation screen/message (no email/SMS) | Yaroslav | Front-end Developer
113 | Sprint 4 | E8 | E8-S1 | Story | As a patient, I want to view upcoming and past appointments, see appointment details, and cancel an appointment.
114 | Sprint 4 | E8 | E8-S1 | Task | API to view and cancel an appointment (patient) | Vanya | Backend Developer
115 | Sprint 4 | E8 | E8-S1 | Task | Patient's appointment list UI with a "Cancel" button | Yana | Front-end Developer
116 | Sprint 4 | E8 | E8-S2 | Story | As a provider, I want to view my appointments and confirm or cancel them.
117 | Sprint 4 | E8 | E8-S2 | Task | Provider-side API: list of appointments, confirm/cancel | Vanya | Backend Developer
118 | Sprint 4 | E8 | E8-S2 | Task | Provider cabinet UI: "My appointments" | Yana | Front-end Developer
119 | Sprint 4 | E2 | E2-S5 | Story | As a patient, I want to see my upcoming and past appointments in my profile, so that I have the full picture. |  |  | Deferred from Sprint 1 - depends on the booking data model
120 | Sprint 4 | E2 | E2-S5 | Task | Endpoint to fetch the patient's list of appointments | Vanya | Backend Developer
121 | Sprint 4 | E2 | E2-S5 | Task | Appointment list UI ("Upcoming"/"Past" tabs) | Yana | Front-end Developer
122 | Sprint 4 | E6 | E6-S1 | Task | Logic to automatically hide booked/unavailable slots from search and booking | Vanya | Backend Developer | Deferred from Sprint 2 - depends on booking data existing
123 | Sprint 4 | Support | support | Task | Provide Vanya with domain context (User/Provider/Availability models) and code review for the integration | Marika | Backend Developer
124 | Sprint 4 | Support | support | Task | Final testing of the license queue and account management | Marika | Backend Developer
125 | Sprint 4 | Support | support | Task | Final infrastructure audit before release | Marika | Backend Developer
126 | Sprint 4 | Design | design | Task | Final visual polish of the booking and confirmation screens | Illia | Designer (UI/UX)
127 | Sprint 4 | Analytics | analytics | Task | Final MVP metrics dashboard (against the acceptance criterion) | Oksana | Data Analyst
128 | Sprint 4 | QA | qa | Task | Full regression testing (Sprint 1-4) | Iryna | QA
129 | Sprint 4 | QA | qa | Task | End-to-end testing of the booking flow | Iryna | QA
130 | Sprint 4 | QA | qa | Task | User acceptance testing (UAT) against the acceptance criterion | Iryna | QA
131 | Sprint 4 | PM | pm | Task | Sprint review & retrospective, demo of the full MVP | Anna | PM
132 | Sprint 4 | PM | pm | Task | Release/deployment preparation | Anna | PM
133 | Backlog | E11 | e11-post-mvp | Backlog item | Clinic/hospital networks and a Hospital Admin role |  |  | Not scheduled - Post-MVP / Future backlog
134 | Backlog | E11 | e11-post-mvp | Backlog item | Administrator management of appointment bookings |  |  | Not scheduled - Post-MVP / Future backlog
135 | Backlog | E11 | e11-post-mvp | Backlog item | Rescheduling an appointment as a separate feature |  |  | Not scheduled - Post-MVP / Future backlog
136 | Backlog | E11 | e11-post-mvp | Backlog item | Geolocation-based search/sorting by distance, interactive map |  |  | Not scheduled - Post-MVP / Future backlog
137 | Backlog | E11 | e11-post-mvp | Backlog item | Automated license verification via an external registry/API |  |  | Not scheduled - Post-MVP / Future backlog
138 | Backlog | E11 | e11-post-mvp | Backlog item | Email/SMS/push notifications |  |  | Not scheduled - Post-MVP / Future backlog
139 | Backlog | E11 | e11-post-mvp | Backlog item | Payments/billing |  |  | Not scheduled - Post-MVP / Future backlog
140 | Backlog | E11 | e11-post-mvp | Backlog item | Full legal compliance with HIPAA/GDPR (DPIA, signed BAAs) |  |  | Not scheduled - Post-MVP / Future backlog
141 | Backlog | E11 | e11-post-mvp | Backlog item | Reviews & ratings, multilingual content, pregnancy timeline/checklist, midwife search, birth-center search |  |  | Not scheduled - Post-MVP / Future backlog

## Team Workload
Assignee | Role | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Total
Anna | PM | 3 | 2 | 3 | 2 | 10
Illia | Designer (UI/UX) | 2 | 1 | 2 | 1 | 6
Yana | Front-end Developer | 7 | 2 | 3 | 3 | 15
Yaroslav | Front-end Developer | 7 | 3 | 2 | 2 | 14
Marika | Backend Developer | 14 | 12 | 5 | 3 | 34
Vanya | Backend Developer | 0 | 0 | 0 | 6 | 6
Iryna | QA | 3 | 2 | 3 | 3 | 11
Oksana | Data Analyst | 1 | 1 | 1 | 1 | 4
Total |  | 37 | 23 | 19 | 21 | 100

## Legend & Labels
LABELING SCHEME (for free Jira, where Task cannot have a Story as Parent)
Every User Story gets a label in the form "{Epic}-S{n}" (e.g. E1-S1, E2-S3). Apply the same label to the Story issue AND to every Task/Sub-task that implements it. Set the Epic Link/Parent on both the Story and its Tasks to the SAME Epic (E1-E11). This lets you filter/group by label in the Backlog to see which Tasks belong to which Story, even though Jira Free has no direct Story-to-Task parent link.
For E4 (Search & Filtering) and E6 (Availability Management), several User Stories share the same implementation Tasks (they will be delivered together as one feature slice), so all of them carry one combined label: E4-S1 and E6-S1 respectively.
Work streams that are not part of the original E1-E11 backlog (Design, Analytics, QA, PM, Integration, Support) use a simple domain label instead: design, analytics, qa, pm, integration, support. In Jira these can be modeled as small standalone Epics, or simply as Tasks with that label and no Epic Link.
E11 (Post-MVP / Future backlog) items use a single shared label "e11-post-mvp" and are not assigned to any sprint.
WORK-ASSIGNMENT ASSUMPTIONS
1. Backend: Marika owns all backend work except the Appointment Booking domain (Epic E7) and the closely related parts of E8 and E2-S5 (viewing appointments) - that whole block is handed to Vanya, who joins the team in Sprint 4. In Sprint 4, Marika takes a supporting role: code review of the integration, final testing of already-built modules (E9, E10), and the final infrastructure audit.
2. Frontend work is distributed between Yana and Yaroslav to balance workload as evenly as possible, both in total and per sprint, while keeping closely related tasks within the same feature together where practical (e.g. a Task and its own Sub-tasks stay with one owner). It is not a strict split by page or by "manage vs. discover" - either developer may pick up a task on any of the 4 pages if that keeps the load balanced.
3. Story issues in the table have no personal assignee - they are the grouping level; the actual work and ownership are recorded at the Task/Sub-task level.
4. All Epic names and User Story / Task / Sub-task wording for E1-E11 are quoted exactly from the source document "Backlog_and_Sitemap_EN.docx".
SPRINT 1 REBALANCING (fix applied after review)
An earlier version of this plan left Yaroslav unassigned in Sprint 1, overloaded Marika with 20 items, and gave Yana far more front-end work overall than Yaroslav (20 vs 9). This has been corrected in two ways. First, Yaroslav now starts building the Search & Results and Provider Details page UI in Sprint 1 against mock data and the Sprint 1 wireframes (labels E4-S1/E5-S1), instead of waiting idle until their backend endpoints exist in Sprint 2; these are then wired to the live endpoints early in Sprint 2. Second, several Sprint 1 front-end tasks that do not need to stay with Yana for feature-cohesion reasons (the login form, the new-password form, and the patient's location/language/pregnancy-week fields) were reassigned to Yaroslav, bringing the front-end split to roughly 15 (Yana) / 14 (Yaroslav) overall, and 7/7 in Sprint 1 specifically. On the backend side, two lower-priority items have been pushed out of Sprint 1: the license-submission story E3-S3 now ships in Sprint 2 together with the E9-S1 license-review queue it depends on, and the password-reset story E1-S5's backend tasks move to Sprint 3, since password reset is not required for the core acceptance-criterion demo flow. Marika's Sprint 1 load drops from 20 to 14 items. Full parity across all sprints is not achievable while Marika remains the only backend developer through Sprint 3 - the goal here is a realistic, reduced front-loading rather than an artificial even split.